## Matrix
Matrice RACI |  | Projet Manimal
|  | ROLES | Client | Chef de Projet | Technicien Niv. 3 | Responsable Logistics | Formateur | Assistant Logistics | Admin Windows | Expert CyberSec | Technicien Orange | Monteur meuble IKEA
| Tâches | Status | Sponsor / Responsable |  |  |  | Equipe Projet |  |  |  | Autres Ressources
Conception
| Préparation de Cahier des charges |  | R | A | R | R |  | I | I | I
| Choix de matériels |  | R | R | A | C |  | I
Planification
| Commande & Réception des matériels |  | I |  |  | A |  | A
| Réception des meubles |  |  | A | [7 empty] | R
| Configuration téléphone |  |  |  | A |  |  | I |  | I | R
| Préparation d'installation |  |  | A | R | C |  | R | I | I
Réalisation
| Installation des postes |  |  | A | R | C |  | R
| Installation Serveurs |  |  | A | R |  |  |  | R
| Installation des téléphones |  |  |  | A | [5 empty] | R
| Configuration Routage |  |  |  | R
| Active Directory |  |  | I | A |  |  |  | R
| Configuration SIP |  |  | A | R
| Configuration serveur DHCP |  |  | A | R | I |  | I | R | I
| Configuration serveur DNS |  |  |  | R | I |  | I | R | I
| Configuration CyberSec |  |  | A | I | I |  | I | I | R
Terminaison
| Test de serveur partagé |  |  | A | R | C |  | R | R | I
| Prép Guide d'utilisateurs |  |  | A | I | I | R
| Formation Users |  |  | A |  |  | R |  | C
R | Réaliser
A | Superviser
C | Conseiller
I | est informé

## About
RACI MATRIX TEMPLATE by Vertex42.com
https://www.vertex42.com/ExcelTemplates/raci-matrix.html
© 2018 Vertex42 LLC
About This Template
Use this template within your project team to help clarify and communicate roles and responsibilities for each task or deliverable. Start by inserting rows to define the tasks and deliverables and insert columns as needed to define the roles of sponsors, leaders, consultants, and project team members. Customize the abbreviations below the chart based on the method you are using (RACI, DRASCI, CAIRO, etc.).
Terms of Use / Copyright
This template is a copyrighted work. Do not submit copies or modifications of this template to any website or online template gallery. Click on the link below to learn how you may or may not use this template.
License: Private Use Only
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.